## Menu
PROJECT MANAGEMENT KPI DASHBOARD
MENU
INPUT | OUTPUT
METRIC SETTINGS
CURRENT YEAR ACTUALS
CURRENT YEAR TARGETS
PREVIOUS YEAR ACTUALS
TRENDS & CHARTS
MONTHLY DASHBOARD

## Metrics
PROJECT MANAGEMENT KPI DASHBOARD
KPI METRICS
KPI Code | KPI Group | Criteria | Unit | Lower Better? | Cumulative Calculation Method? | KPI Description | STARTING DATE SETTING
101 | Budget | Planned Value (PV) | USD | No | Sum | The amount is estimated and agreed-upon budget for a particular project that must be accomplished within the budget. | Year | 2022
102 | Budget | Actual Cost (AC) | USD | Yes | Sum | The revenue has already been used in achieving the current completion percentage. | Month | January
103 | Budget | Earned Value (EV) | USD | No | Sum | The budget for all project activities carried out until a certain date.
104 | Budget | Cost Variance (CV) | USD | No | Average | The amount in the end of project shows what is the percentage of assumed at the beginning cost.
105 | Budget | Cost Performance Index (CPI) | # | No | Average | The ratio between earned value and actual cost.
106 | Budget | Return on Investment (ROI) | % | No | Average | The percentage that shows the return, return on the investment made.
107 | Budget | Gross Profit Margin (Margin) | % | No | Average | The amount left over from a business's income after direct selling expenses are subtracted.
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | No | Average | The amount that shows how far ahead or behind the planned budget and the planned work the project.
202 | Schedule | Schedule Performance Index (SPI) | # | No | Average | The ratio between earned value and planned value.
203 | Schedule | Planned Vs Actual Work Hours | % | No | Average | The variance between the hours still needed to complete the job and the future hours currently in planning.
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | % | No | Average | The percentage used to manage project resources and monitor project and portfolio health.
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | % | Yes | Average | The number of overdue tasks out of number of all tasks in given project.
303 | Effectiveness | Missed Milestones Ratio | % | Yes | Average | The number of overdue milestones out of number of all milestones in given project.
304 | Effectiveness | Percentage Of Tasks Completed | % | No | Average | The ratio of completed within all started tasks in some period of time.
305 | Effectiveness | Tasks % Completed On Time | % | No | Average | The percentage showing the number of tasks completed by each employee over a given period of time.
306 | Effectiveness
307 | Effectiveness
Back to
Menu

## CY_Actual
PROJECT MANAGEMENT KPI DASHBOARD
CURRENT YEAR ACTUALS
KPI Code | KPI Group | Criteria | Unit | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022
101 | Budget | Planned Value (PV) | USD | 65475 | 68748.75 | 70811.2125 | 66562.5398 | 71221.9175 | 69085.26
102 | Budget | Actual Cost (AC) | USD | 30830.8 | 33297.264 | 32631.3187 | 31326.066 | 30386.284 | 27347.6556
103 | Budget | Earned Value (EV) | USD | 21780 | 21997.8 | 23097.69 | 21942.8055 | 23698.2299 | 23224.2653
104 | Budget | Cost Variance (CV) | USD | 1.045 | 1.012 | 1.034 | 1.056 | 1.078 | 1.067
105 | Budget | Cost Performance Index (CPI) | # | 0.89424 | 0.87636 | 0.891 | 0.855 | 0.882 | 0.819
106 | Budget | Return on Investment (ROI) | % | 122.6% | 121.4% | 109.3% | 98.33% | 91.45% | 92.36%
107 | Budget | Gross Profit Margin (Margin) | % | 28.27% | 29.68% | 31.76% | 30.49% | 27.44% | 29.91%
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 13365 | 14567.85 | 15004.8855 | 14404.6901 | 15557.0653 | 15712.6359
202 | Schedule | Schedule Performance Index (SPI) | # | 0.75816 | 0.80365 | 0.82776 | 0.86087 | 0.82643 | 0.85123
203 | Schedule | Planned Vs Actual Work Hours | % | 89.1% | 90.9% | 99% | 114.3% | 102.9% | 102.9%
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
Back to
Menu
CUMULATIVE TOTALS
(CY ACTUALS)
Add / Edit Metrics

## CY_Target
PROJECT MANAGEMENT KPI DASHBOARD
CURRENT YEAR TARGETS
KPI Code | KPI Group | Criteria | Unit | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022
101 | Budget | Planned Value (PV) | USD | 75000 | 75000 | 75000 | 75000 | 75000 | 75000
102 | Budget | Actual Cost (AC) | USD | 30800 | 30800 | 30800 | 30800 | 30800 | 30800
103 | Budget | Earned Value (EV) | USD | 22000 | 22000 | 22000 | 22000 | 22000 | 22000
104 | Budget | Cost Variance (CV) | USD | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947
105 | Budget | Cost Performance Index (CPI) | # | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92
106 | Budget | Return on Investment (ROI) | % | 125% | 125% | 125% | 125% | 125% | 125%
107 | Budget | Gross Profit Margin (Margin) | % | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1%
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 16500 | 16500 | 16500 | 16500 | 16500 | 16500
202 | Schedule | Schedule Performance Index (SPI) | # | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78
203 | Schedule | Planned Vs Actual Work Hours | % | 113% | 113% | 113% | 113% | 113% | 113%
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
CUMULATIVE TOTALS
(CY TARGETS)
Back to
Menu
Add / Edit Metrics

## PY_Actual
PROJECT MANAGEMENT KPI DASHBOARD
PREVIOUS YEAR ACTUALS
KPI Code | KPI Group | Criteria | Unit | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021
101 | Budget | Planned Value (PV) | USD | 76500 | 63000 | 60750 | 68250 | 68250 | 66750
102 | Budget | Actual Cost (AC) | USD | 34496 | 35728 | 35420 | 31108 | 29568 | 30184
103 | Budget | Earned Value (EV) | USD | 25740 | 24420 | 22880 | 24640 | 23760 | 25740
104 | Budget | Cost Variance (CV) | USD | 1.0606 | 1.0133 | 1.0322 | 1.0606 | 1.1175 | 1.0701
105 | Budget | Cost Performance Index (CPI) | # | 0.7728 | 0.8924 | 0.8188 | 0.8372 | 0.9108 | 0.874
106 | Budget | Return on Investment (ROI) | % | 102.5% | 128.8% | 101.3% | 123.8% | 117.5% | 131.2%
107 | Budget | Gross Profit Margin (Margin) | % | 32.66% | 31.41% | 29.23% | 25.19% | 30.48% | 32.66%
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 13200 | 15015 | 16335 | 16335 | 16665 | 13365
202 | Schedule | Schedule Performance Index (SPI) | # | 0.7098 | 0.6474 | 0.7878 | 0.6708 | 0.7176 | 0.6552
203 | Schedule | Planned Vs Actual Work Hours | % | 115.3% | 101.7% | 100.6% | 106.2% | 102.8% | 108.5%
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
CUMULATIVE TOTALS
(PY ACTUALS)
Back to
Menu
Add / Edit Metrics

## CY_Actual_Cumulative
PROJECT MANAGEMENT KPI DASHBOARD
CURRENT YEAR ACTUALS - CUMULATIVE
KPI Code | KPI Group | Criteria | Unit | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022
101 | Budget | Planned Value (PV) | USD | 65475 | 134223.75 | 205034.9625 | 271597.5023 | 342819.4198 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798
102 | Budget | Actual Cost (AC) | USD | 30830.8 | 64128.064 | 96759.3827 | 128085.4487 | 158471.7327 | 185819.3883 | 185819.3883 | 185819.3883 | 185819.3883 | 185819.3883 | 185819.3883 | 185819.3883
103 | Budget | Earned Value (EV) | USD | 21780 | 43777.8 | 66875.49 | 88818.2955 | 112516.5254 | 135740.7908 | 135740.7908 | 135740.7908 | 135740.7908 | 135740.7908 | 135740.7908 | 135740.7908
104 | Budget | Cost Variance (CV) | USD | 1.045 | 1.0285 | 1.0303 | 1.0368 | 1.045 | 1.0487 | 1.0487 | 1.0487 | 1.0487 | 1.0487 | 1.0487 | 1.0487
105 | Budget | Cost Performance Index (CPI) | # | 0.89424 | 0.8853 | 0.8872 | 0.87915 | 0.87972 | 0.8696 | 0.8696 | 0.8696 | 0.8696 | 0.8696 | 0.8696 | 0.8696
106 | Budget | Return on Investment (ROI) | % | 122.6% | 122% | 117.8% | 112.9% | 108.6% | 105.9% | 105.9% | 105.9% | 105.9% | 105.9% | 105.9% | 105.9%
107 | Budget | Gross Profit Margin (Margin) | % | 28.27% | 28.98% | 29.9% | 30.05% | 29.53% | 29.59% | 29.59% | 29.59% | 29.59% | 29.59% | 29.59% | 29.59%
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 13365 | 13966.425 | 14312.5785 | 14335.6064 | 14579.8982 | 14768.6878 | 14768.6878 | 14768.6878 | 14768.6878 | 14768.6878 | 14768.6878 | 14768.6878
202 | Schedule | Schedule Performance Index (SPI) | # | 0.75816 | 0.7809 | 0.79652 | 0.81261 | 0.81537 | 0.82135 | 0.82135 | 0.82135 | 0.82135 | 0.82135 | 0.82135 | 0.82135
203 | Schedule | Planned Vs Actual Work Hours | % | 89.1% | 90% | 93% | 98.32% | 99.23% | 99.84% | 99.84% | 99.84% | 99.84% | 99.84% | 99.84% | 99.84%
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
Back to
Menu

## CY_Target_Cumulative
PROJECT MANAGEMENT KPI DASHBOARD
CURRENT YEAR TARGETS - CUMULATIVE
KPI Code | KPI Group | Criteria | Unit | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022
101 | Budget | Planned Value (PV) | USD | 75000 | 150000 | 225000 | 300000 | 375000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
102 | Budget | Actual Cost (AC) | USD | 30800 | 61600 | 92400 | 123200 | 154000 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800 | 184800
103 | Budget | Earned Value (EV) | USD | 22000 | 44000 | 66000 | 88000 | 110000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000 | 132000
104 | Budget | Cost Variance (CV) | USD | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947 | 0.947
105 | Budget | Cost Performance Index (CPI) | # | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92 | 0.92
106 | Budget | Return on Investment (ROI) | % | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125% | 125%
107 | Budget | Gross Profit Margin (Margin) | % | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1% | 31.1%
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500 | 16500
202 | Schedule | Schedule Performance Index (SPI) | # | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78 | 0.78
203 | Schedule | Planned Vs Actual Work Hours | % | 113% | 113% | 113% | 113% | 113% | 113% | 113% | 113% | 113% | 113% | 113% | 113%
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
Back to
Menu

## PY_Actual_Cumulative
PROJECT MANAGEMENT KPI DASHBOARD
PREVIOUS YEAR ACTUALS - CUMULATIVE
KPI Code | KPI Group | Criteria | Unit | Jan 2021 | Feb 2021 | Mar 2021 | Apr 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021
101 | Budget | Planned Value (PV) | USD | 76500 | 139500 | 200250 | 268500 | 336750 | 403500 | 403500 | 403500 | 403500 | 403500 | 403500 | 403500
102 | Budget | Actual Cost (AC) | USD | 34496 | 70224 | 105644 | 136752 | 166320 | 196504 | 196504 | 196504 | 196504 | 196504 | 196504 | 196504
103 | Budget | Earned Value (EV) | USD | 25740 | 50160 | 73040 | 97680 | 121440 | 147180 | 147180 | 147180 | 147180 | 147180 | 147180 | 147180
104 | Budget | Cost Variance (CV) | USD | 1.0606 | 1.037 | 1.0354 | 1.0417 | 1.0569 | 1.0591 | 1.0591 | 1.0591 | 1.0591 | 1.0591 | 1.0591 | 1.0591
105 | Budget | Cost Performance Index (CPI) | # | 0.7728 | 0.8326 | 0.828 | 0.8303 | 0.8464 | 0.851 | 0.851 | 0.851 | 0.851 | 0.851 | 0.851 | 0.851
106 | Budget | Return on Investment (ROI) | % | 102.5% | 115.6% | 110.8% | 114.1% | 114.8% | 117.5% | 117.5% | 117.5% | 117.5% | 117.5% | 117.5% | 117.5%
107 | Budget | Gross Profit Margin (Margin) | % | 32.66% | 32.03% | 31.1% | 29.62% | 29.79% | 30.27% | 30.27% | 30.27% | 30.27% | 30.27% | 30.27% | 30.27%
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 13200 | 14107.5 | 14850 | 15221.25 | 15510 | 15152.5 | 15152.5 | 15152.5 | 15152.5 | 15152.5 | 15152.5 | 15152.5
202 | Schedule | Schedule Performance Index (SPI) | # | 0.7098 | 0.6786 | 0.715 | 0.70395 | 0.70668 | 0.6981 | 0.6981 | 0.6981 | 0.6981 | 0.6981 | 0.6981 | 0.6981
203 | Schedule | Planned Vs Actual Work Hours | % | 115.3% | 108.5% | 105.8% | 105.9% | 105.3% | 105.8% | 105.8% | 105.8% | 105.8% | 105.8% | 105.8% | 105.8%
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
Back to
Menu

## Monthly_Analysis
PROJECT MANAGEMENT KPI DASHBOARD
MONTHLY DASHBOARD
Month | Apr 2022 |  |  | Monthly |  |  |  |  | Cumulative
KPI Code | KPI Group | Criteria | Unit | Previous Year | Target | Actual | Act vs. PY Index | Act vs. Trgt Index | Previous Year | Target | Actual | Act vs. PY Index | Act vs. Trgt Index
101 | Budget | Planned Value (PV) | USD | 68250 | 75000 | 66562.5398 | 97.5275 | 88.7501 | 268500 | 300000 | 271597.5023 | 101.1536 | 90.5325
102 | Budget | Actual Cost (AC) | USD | 31108 | 30800 | 31326.066 | 99.3039 | 98.3207 | 136752 | 123200 | 128085.4487 | 106.7662 | 96.1858
103 | Budget | Earned Value (EV) | USD | 24640 | 22000 | 21942.8055 | 89.0536 | 99.74 | 97680 | 88000 | 88818.2955 | 90.9278 | 100.9299
104 | Budget | Cost Variance (CV) | USD | 1.0606 | 0.947 | 1.056 | 99.5625 | 111.51 | 1.0417 | 0.947 | 1.0368 | 99.5248 | 109.4773
105 | Budget | Cost Performance Index (CPI) | # | 0.8372 | 0.92 | 0.855 | 102.1261 | 92.9348 | 0.8303 | 0.92 | 0.87915 | 105.8833 | 95.5597
106 | Budget | Return on Investment (ROI) | % | 123.8% | 125% | 98.33% | 79.461 | 78.6664 | 114.1% | 125% | 112.9% | 98.9842 | 90.3231
107 | Budget | Gross Profit Margin (Margin) | % | 25.19% | 31.1% | 30.49% | 121.0384 | 98.0411 | 29.62% | 31.1% | 30.05% | 101.4468 | 96.6281
108 | Budget
109 | Budget
201 | Schedule | Scheduled Variance (SV) | USD | 16335 | 16500 | 14404.6901 | 88.183 | 87.3012 | 15221.25 | 16500 | 14335.6064 | 94.1815 | 86.8825
202 | Schedule | Schedule Performance Index (SPI) | # | 0.6708 | 0.78 | 0.86087 | 128.3347 | 110.3679 | 0.70395 | 0.78 | 0.81261 | 115.4357 | 104.1807
203 | Schedule | Planned Vs Actual Work Hours | % | 106.2% | 113% | 114.3% | 107.6 | 101.144 | 105.9% | 113% | 98.32% | 92.8125 | 87.0117
204 | Schedule
205 | Schedule
301 | Effectiveness | Resource Utilization | %
302 | Effectiveness | Overdue Tasks / Crossed Deadlines | %
303 | Effectiveness | Missed Milestones Ratio | %
304 | Effectiveness | Percentage Of Tasks Completed | %
305 | Effectiveness | Tasks % Completed On Time | %
306 | Effectiveness
307 | Effectiveness
Choose Month
Back to
Menu

## KPI_Analysis
PROJECT MANAGEMENT KPI DASHBOARD
TRENDS & CHARTS
101 : Budget / Planned Value (PV)
|  | Jan 2022 | Feb 2022 | Mar 2022 | Apr 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 | Oct 2022 | Nov 2022 | Dec 2022
Monthly | Previous Year | 76500 | 63000 | 60750 | 68250 | 68250 | 66750 | 0 | 0 | 0 | 0 | 0 | 0
| Target | 75000 | 75000 | 75000 | 75000 | 75000 | 75000 | 0 | 0 | 0 | 0 | 0 | 0
| Actual | 65475 | 68748.75 | 70811.2125 | 66562.5398 | 71221.9175 | 69085.26 | 0 | 0 | 0 | 0 | 0 | 0
| Act./Target Index | 87.3 | 91.665 | 94.415 | 88.7501 | 94.9626 | 92.1137
Cumulative | PY Cum | 76500 | 139500 | 200250 | 268500 | 336750 | 403500 | 403500 | 403500 | 403500 | 403500 | 403500 | 403500
| Target Cum | 75000 | 150000 | 225000 | 300000 | 375000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000 | 450000
| Actual Cum | 65475 | 134223.75 | 205034.9625 | 271597.5023 | 342819.4198 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798 | 411904.6798
| Act./Target Index | 87.3 | 89.4825 | 91.1267 | 90.5325 | 91.4185 | 91.5344 | 91.5344 | 91.5344 | 91.5344 | 91.5344 | 91.5344 | 91.5344
Select KPI
Back to
Menu

## Calc (hidden)
Date Settings |  | Month Order |  |  |  |  | General Calculations |  | The Criteria's |  |  |  | Print Area
Starting Year | 2022 | Order | Year | Month | Current Year | Previous Year | Cumulative Options | Better Low Options | Criteria's Without Blanks | KPI Group | KPI Code | Dropdown Menu | Dimension
Starting Month | January | 1 | 2022 | January | Jan 2022 | Jan 2021 | Average | Yes | Planned Value (PV) | Budget | 101 | 101 : Budget / Planned Value (PV) | Height | 18
Month Index | 1 | 2 | 2022 | February | Feb 2022 | Feb 2021 | Sum | No | Actual Cost (AC) | Budget | 102 | 102 : Budget / Actual Cost (AC) | Width | 16
|  | 3 | 2022 | March | Mar 2022 | Mar 2021 |  |  | Earned Value (EV) | Budget | 103 | 103 : Budget / Earned Value (EV)
January | Jan | 4 | 2022 | April | Apr 2022 | Apr 2021 | Dashboard Selected Date | Apr 2022 | Cost Variance (CV) | Budget | 104 | 104 : Budget / Cost Variance (CV)
February | Feb | 5 | 2022 | May | May 2022 | May 2021 | Dashboard Previous Year | Apr 2021 | Cost Performance Index (CPI) | Budget | 105 | 105 : Budget / Cost Performance Index (CPI)
March | Mar | 6 | 2022 | June | Jun 2022 | Jun 2021 |  |  | Return on Investment (ROI) | Budget | 106 | 106 : Budget / Return on Investment (ROI)
April | Apr | 7 | 2022 | July | Jul 2022 | Jul 2021 | Criteria Number | 10 | Gross Profit Margin (Margin) | Budget | 107 | 107 : Budget / Gross Profit Margin (Margin)
May | May | 8 | 2022 | August | Aug 2022 | Aug 2021 |  |  | Scheduled Variance (SV) | Schedule | 201 | 201 : Schedule / Scheduled Variance (SV)
June | Jun | 9 | 2022 | September | Sep 2022 | Sep 2021 | Charts Selected Criteria | Planned Value (PV) | Schedule Performance Index (SPI) | Schedule | 202 | 202 : Schedule / Schedule Performance Index (SPI)
July | Jul | 10 | 2022 | October | Oct 2022 | Oct 2021 | Charts Selected Low Better Option | No | Planned Vs Actual Work Hours | Schedule | 203 | 203 : Schedule / Planned Vs Actual Work Hours
August | Aug | 11 | 2022 | November | Nov 2022 | Nov 2021
September | Sep | 12 | 2022 | December | Dec 2022 | Dec 2021 | Last Row | 15
October | Oct
November | Nov
December | Dec | [5 empty] | Doughnut Charts
[7 empty] | Cumulative Index - Target Chart | 91.53%
[7 empty] | Remaining | 8.466%