## Dashboard
PERT CHART GENERATOR TEMPLATE
DASHBOARD
PERT CHART DATA | [13 empty] | SETTINGS PANEL
ID | Description | Predecessors Previous ID | Phase (Optional) | O Optimistic Time | P Pessimistic Time | M Most likely Time | Duration (Expected) | Early Start | Early Finish | Late Start | Late Finish | Slack | Shape Color (Optional) |  | Messages
1 | Start | [5 empty] | 0 | 0 | 0 | 4.4409e-16 | 4.4409e-16 | 0 | Blue
2 | First project meeting | 1 |  | 2 | 3 | 2.2 | 2.3 | 0 | 2.3 | 4.4409e-16 | 2.3 | 0 | Green |  | Ready! Click the button to Create your Chart.
3 | Target Market Acquired | 2 |  | 3 | 3.5 | 3 | 3.0833 | 2.3 | 5.3833 | 3.65 | 6.7333 | 1.35 | Green
4 | Design Approved | 2,5 |  | 3 | 3.6 | 3.2 | 3.2333 | 3.3333 | 6.5667 | 3.3333 | 6.5667 | 0 | Yellow
5 | Content Drafted | 2 | A | 1 | 1.2 | 1 | 1.0333 | 2.3 | 3.3333 | 2.3 | 3.3333 | 0 | Purple |  |  | SHAPE SETTINGS
6 | Marketing materials Create | 3 |  | 2 | 3 | 2.5 | 2.5 | 5.3833 | 7.8833 | 6.7333 | 9.2333 | 1.35 | Orange
7 | Website Complete | 4 |  | 2 | 4 | 2.5 | 2.6667 | 6.5667 | 9.2333 | 6.5667 | 9.2333 | 0 | Yellow |  |  | Chart Layout: | Horizontal
8 | Finalized Content | 5 | A | 2 | 3.5 | 2.5 | 2.5833 | 3.3333 | 5.9167 | 6.65 | 9.2333 | 3.3167 | Green |  |  | Full Information: | Yes
9 | Finalized Website | 6,7,8 |  | 1 | 1.3 | 1 | 1.05 | 9.2333 | 10.2833 | 9.2333 | 10.2833 | 0 | Orange |  |  | Critical tasks: | Highlight
10 | End | 9 |  |  |  |  | 0 | 10.2833 | 10.2833 | 10.2833 | 10.2833 | 0 | Blue
[16 empty] | Shape Width Zoom: | 0.8
[16 empty] | Shape Height Zoom: | 0.8
[16 empty] | Shapes Gap (horizontal): | 40
[16 empty] | Shapes Gap (vertical): | 30
[16 empty] | Connectors: | Straight
[16 empty] | Font Size: | 10
COLOR SETTINGS
[16 empty] | Selection Names | Color
Blue
Red
Green
Orange
Purple
White
Yellow
Shape Font Color:
Arrow Color:
CREATE CHART
Go to Current Chart
CLEAR EXISTING DATA
Instructions
On
Off

## PERT
PERT CHART GENERATOR TEMPLATE
CHART
Phase - A
Export to PDF
ADJUST
Back to
Menu
Start
0
0
0
0
0
0
First project meeting
0
2,3
2,3
2,3
0
0
Target Market Acquired
2,3
3,1
5,4
6,7
1,4
3,7
Design Approved
3,3
3,2
6,6
6,6
0
3,3
Content Drafted
2,3
1
3,3
3,3
0
2,3
Marketing materials Create
5,4
2,5
7,9
9,2
1,4
6,7
Website Complete
6,6
2,7
9,2
9,2
0
6,6
Finalized Content
3,3
2,6
5,9
9,2
3,3
6,6
Finalized Website
9,2
1
10,3
10,3
0
9,2
End
10,3
0
10,3
10,3
0
10,3

## Calculations (hidden)
[5 empty] | Next ID Formula | [7 empty] | CRITICAL PATH CALCULATION | [18 empty] | REFERENCE | [33 empty] | GRIDS | [14 empty] | POSITION TOWARDS THE PRECEDENT | [9 empty] | GRID | [5 empty] | SHAPES | [12 empty] | ERROR CHECKS
| First Shape: | [64 empty] | Start Grid X | Start Grid Y |  | Process Fallback: | Process Index | [9 empty] | Count Phases | [10 empty] | Phase coordinates |  |  |  | Manual Manipulation |  | Start X Coor. | Start Y Coor. | Max W | Max H | Max Column | Max Row | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | 10 | USER DATA | [28 empty] | Precedents - Previous ID | [10 empty] | Dependents - Next ID | [10 empty] | Row Indexes - of Next ID | [11 empty] | 2 | 2 |  | 99999 | 999 |  |  | Phase side calculations | [6 empty] | 1 | [16 empty] | 50 | 184 | 96 | 64 | 43 | 23 | [7 empty] | Error 1 | Error 2 | Error 3 | Error 4 | Error 5 | Error 6 | Error 7 | Error 8 | Error 9 | Error 10 |  |  | 0
Shapes Name | Shape Index | Valid? | ID | Desc | Predecessors Previous ID | O Optimistic Time | P Pessimistic Time | M Most likely Time | Duration (Expected) | Phase | Shape Type | Shape Color (Optional) | ES | EF | LS | LF | Slack | EF of Precedents | [9 empty] | LS of Successors |  |  | Critical Task | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Total | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Number of Dependents | Number of Precedents | GridX | GridY | Combined X-Y | Highest Precedent Index | Process Order | Level | Side | Side helper | Max side | Phase No | Split Phase | Order in one row | Which Phase | Order in split | Phases List | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | Min X | Min Y | W | H | Shape X Coor. | Shape Y Coor. | Shape X Coor. | Shape Y Coor. | Shape Width | Shape Height | Shape Type Code | Shape Text | Shape Color No | First free X | First Free Y | Symbol User | Symbol Code | Height | Width | Duplicate ID | Next ID Not Matching | Missing ID | Previous ID Not Matching | Shapes Overlap | Missing connection | Max dependencies |  |  | Missing Settings! | Error No | Error Message (max 48 characters) | Formula | Characters
ShapeIndex1 | 1 | Yes | 1 | Start |  | 0 | 0 | 0 | 0 |  | Start | Blue | 0 | 0 | 4.4409e-16 | 4.4409e-16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.4409e-16 | [14 empty] | 2 | [9 empty] | 2 | 2 | [9 empty] | 1 | 0 | 2 | 2 | 50-184 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | - | - | - | - | A | left | [9 empty] | 307 | 70 | 262 | 94 |  |  | 50 | 184 | 96 | 64 | 5 | Start | 1 | 866 | 278 | Start | 5 | 50 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 1 | • Duplicate ID problem! Please use unique IDs. | 0 | 46
ShapeIndex2 | 2 | Yes | 2 | First project meeting | 1 | 2 | 3 | 2.2 | 2.3 |  | Task | Green | 0 | 2.3 | 4.4409e-16 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.65 | 3.3333 | 2.3 | Y | 1 | [9 empty] | 1 | 3 | 4 | 5 | [7 empty] | 3 | 3 | 4 | 5 | [7 empty] | 3 | 1 | 3 | 2 | 186-184 | 1 | 2 | 1 | 0 | 0 | 1 | 0 | - | - | - | - |  | left | left | left | [13 empty] | 186 | 184 | 96 | 64 | 5 | First project meeting | 3 | 866 | 278 | Task | 5 | 40 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 2 | • "Next ID" does not exist! | 0 | 27
ShapeIndex3 | 3 | Yes | 3 | Target Market Acquired | 2 | 3 | 3.5 | 3 | 3.0833 |  | Task | Green | 2.3 | 5.3833 | 3.65 | 6.7333 | 1.35 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.7333 |  |  |  | 2 | [9 empty] | 2 | 6 | [9 empty] | 6 | 6 | [9 empty] | 1 | 1 | 4 | 1 | 322-174 | 2 | 3 | 2 | -1 | -1 | 3 | 0 | 2 | 1 | 2 | 1 |  | left | [14 empty] | 184 | 322 | 174 | 96 | 64 | 5 | Target Market Acquired | 3 | 594 | 362 | End | 5 | 50 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 3 | • Missing ID | 0 | 12
ShapeIndex4 | 4 | Yes | 4 | Design Approved | 2,5 | 3 | 3.6 | 3.2 | 3.2333 |  | Task | Yellow | 3.3333 | 6.5667 | 3.3333 | 6.5667 | 0 | 2.3 | 3.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5667 |  |  | Y | 2 | 5 | [8 empty] | 2 | 7 | [9 empty] | 7 | 7 | [9 empty] | 1 | 2 | 4 | 1 | 322-268 | 2 | 4 | 2 | -1 | 0 | 3 | 0 | 2 | 1 | 2 | 1 |  | left | [14 empty] | 268 | 322 | 268 | 96 | 64 | 5 | Design Approved | 7 | 594 | 362 | Complete Info |  | 64 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 4 | • "Previous ID" does not exist! | 0 | 31
ShapeIndex5 | 5 | Yes | 5 | Content Drafted | 2 | 1 | 1.2 | 1 | 1.0333 | A | Task | Purple | 2.3 | 3.3333 | 2.3 | 3.3333 | 0 | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.65 | 3.3333 |  | Y | 2 | [9 empty] | 2 | 8 | 4 | [8 empty] | 8 | 8 | 4 | [8 empty] | 2 | 1 | 4 | 1 | 322-90 | 2 | 5 | 2 | -1 | 1 | 3 | 5 | 2 | 1 | 1 | 1 |  | left | down | [14 empty] | 322 | 90 | 96 | 64 | 5 | Content Drafted | 5 | 594 | 362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 5 | • Shapes overlap! Use "Next ID Position" to fix. | 0 | 48
ShapeIndex6 | 6 | Yes | 6 | Marketing materials Create | 3 | 2 | 3 | 2.5 | 2.5 |  | Task | Orange | 5.3833 | 7.8833 | 6.7333 | 9.2333 | 1.35 | 5.3833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2333 |  |  |  | 3 | [9 empty] | 3 | 9 | [9 empty] | 9 | 9 | [9 empty] | 1 | 1 | 5 | 1 | 458-174 | 3 | 6 | 3 | -1 | -1 | 1 | 0 | 3 | 1 | 2 | 1 |  | left | [14 empty] | 184 | 458 | 174 | 96 | 64 | 5 | Marketing materials Create | 4 | 594 | 362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 6 | • Shape has no previous or next ID defined | 0 | 42
ShapeIndex7 | 7 | Yes | 7 | Website Complete | 4 | 2 | 4 | 2.5 | 2.6667 |  | Task | Yellow | 6.5667 | 9.2333 | 6.5667 | 9.2333 | 0 | 6.5667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2333 |  |  | Y | 4 | [9 empty] | 4 | 9 | [9 empty] | 9 | 9 | [9 empty] | 1 | 1 | 5 | 1 | 458-268 | 4 | 7 | 3 | -1 | 0 | 1 | 0 | 3 | 1 | 2 | 1 |  | left | [14 empty] | 268 | 458 | 268 | 96 | 64 | 5 | Website Complete | 7 | 594 | 362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 7 | • Maximum dependencies cannot be higher than 10 | 0 | 47
ShapeIndex8 | 8 | Yes | 8 | Finalized Content | 5 | 2 | 3.5 | 2.5 | 2.5833 | A | Task | Green | 3.3333 | 5.9167 | 6.65 | 9.2333 | 3.3167 | 3.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.2333 |  |  |  | 5 | [9 empty] | 5 | 9 | [9 empty] | 9 | 9 | [9 empty] | 1 | 1 | 5 | 1 | 458-90 | 5 | 8 | 3 | -1 | 1 | 1 | 5 | 3 | 1 | 1 | 1 |  | left | [15 empty] | 458 | 90 | 96 | 64 | 5 | Finalized Content | 3 | 594 | 362 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 8 |  | 0 | 0
ShapeIndex9 | 9 | Yes | 9 | Finalized Website | 6,7,8 | 1 | 1.3 | 1 | 1.05 |  | Task | Orange | 9.2333 | 10.2833 | 9.2333 | 10.2833 | 0 | 7.8833 | 9.2333 | 5.9167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.2833 |  |  | Y | 6 | 7 | 8 | [7 empty] | 6 | 10 | [9 empty] | 10 | 10 | [9 empty] | 1 | 3 | 6 | 2 | 594-184 | 6 | 9 | 4 | 0 | 0 | 1 | 0 | - | - | - | - |  | left | [15 empty] | 594 | 184 | 96 | 64 | 5 | Finalized Website | 4 | 866 | 278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 9 |  | 0 | 0
ShapeIndex10 | 10 | Yes | 10 | End | 9 | 0 | 0 | 0 | 0 |  | End | Blue | 10.2833 | 10.2833 | 10.2833 | 10.2833 | 0 | 10.2833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 9 | [9 empty] | 9 | [21 empty] | 0 | 1 | 7 | 2 | 730-184 | 9 | 10 | 5 | 0 | 0 | 1 | 0 | - | - | - | - | [17 empty] | 730 | 184 | 96 | 64 | 5 | End | 1 | 866 | 278 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 10 | • Missing or Incorrect Settings! | 0 | 32
| - | - | - | - | - | - | - | - | - |  | - | - | [19 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | --- | - |  | - | - | - | - | - | - | - | - | - | [17 empty] | - | - | - | - | - | - | - | - | - | bar: Error 1 to Error 10
| - | - | - | - | - | - | - | - | - |  | - | - | [19 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | --- | - |  | - | - | - | - | - | - | - | - | - | [17 empty] | - | - | - | - | - | - | - | - | - | [15 empty] | Message List | bar: Error 1 to Error 10
| - | - | - | - | - | - | - | - | - |  | - | - | [19 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | --- | - |  | - | - | - | - | - | - | - | - | - | [17 empty] | - | - | - | - | - | - | - | - | - | bar: Error 1 to Error 10
| - | - | - | - | - | - | - | - | - |  | - | - | [19 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | --- | - |  | - | - | - | - | - | - | - | - | - | [17 empty] | - | - | - | - | - | - | - | - | - | [15 empty] | Ready! Click the button to Create your Chart. | bar: Error 1 to Error 10
| - | - | - | - | - | - | - | - | - |  | - | - | [19 empty] | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  |  | --- | - |  | - | - | - | - | - | - | - | - | - | [17 empty] | - | - | - | - | - | - | - | - | - | bar: Error 1 to Error 10
-
[53 empty] | 4 | [67 empty] | Successors Next ID
Predecessors Previous ID
5
4
7
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
5
8
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
[42 empty] | - | [10 empty] | -
3