## Menu
PROJECT PLAN TEMPLATE
MENU
Settings
| Expense Categories | Phases | Priority Levels | Status | Gantt Color
| Labor | Phase 1 | Low | Not Started
| Marketing | Phase 2 | Medium | In-Progress
| Equipment | Phase 3 | High | Completed
| Hardware | Phase 4
| Software | Phase 5
TASK PLANNER
BUDGET PLANNER
DASHBOARD
GANTT VIEW
REPORT FORM

## TaskPlanner
PROJECT PLAN TEMPLATE
TASK PLANNER
Phase | Tasks/Deliverables | Description | Priority | Assigned To | Start Date | Duration [Days] | End Date | Status
Phase 1 | Define Scope | Determine project scope and goals | Low | Alice | 2024-01-02 | 5 | 2024-01-06 | Not Started
Phase 1 | Identify Stakeholders | List all stakeholders | Medium | Bob | 2024-01-01 | 3 | 2024-01-03 | In-Progress
Phase 2 | Create Schedule | Develop project timeline | High | Charlie | 2024-01-07 | 7 | 2024-01-13 | Completed
Phase 2 | Resource Planning | Allocate resources | Low | Diana | 2024-01-08 | 5 | 2024-01-12
Phase 3 | Task Execution | Execute project tasks | Medium | Entire Team | 2024-01-15 | 20 | 2024-02-03 | Completed
Phase 3 | Monitor Progress | Track task progress | Medium | Emma | 2024-01-16 | 20 | 2024-02-04 | Not Started
Phase 3 | Risk Management | Identify and mitigate risks | High | Frank | 2024-01-20 | 10 | 2024-01-29 | In-Progress
Formulas:
End Date = IFERROR(IF(OR(LEN([Start Date])=0,LEN([Tasks/Deliverables])=0),"",[Start Date]+[Duration [Days]]-1),"")
Back to
Menu

## Budget
PROJECT PLAN
BUDGET
COST ESTIMATIONS |  | 178000 | ACTUAL COSTS |  |  | 123000
Expense Category | Description | Budget | Expense Category | Description | Date | Spent
Labor | Developers | 30000 | Labor | Developers | 2024-01-10 | 10000
Labor | Project Manager | 5000 | Labor | Project Manager | 2024-01-12 | 2000
Labor | Designers | 20000 | Hardware | Computers | 2024-01-05 | 60000
Hardware | Computers | 50000 | Marketing | Printables | 2024-01-15 | 2000
Software | Licenses | 10000 | Marketing | Advertising | 2024-01-20 | 20000
Marketing | Advertising | 40000 | Equipment | Printer | 2024-06-01 | 22000
Marketing | Printables | 3000 | Software | Licenses | 2024-06-20 | 7000
Equipment | Printer | 20000
Back to
Menu

## Report
PROJECT PLAN TEMPLATE
REPORT
| PROJECT PLAN |  |  |  | Report Date:
| Work Load Web App Project |  |  |  | 2024-01-10
PROJECT SCOPE
This project aims to develop a new mobile app. The app will aim to help employees to plan their daily work load.
The target audience will be 30-45 year-old while collar employees.
PROJECT OBJECTIVES
Prepare a mobile app with full functionality. This app will be a base for future improvements.
The app will help users to plan their daily work load.
TEAM
| PROJECT MANAGER |  | Responsible:
| Danny J. Lewis |  | Plan and manage all the process and report to the top management.
Monitor the progress of all tasks.
| MARKETING MANAGER |  | Responsible:
| Mary Dewill |  | Manage and track ad campaigns.
Outsource marketing labor for preparing the printables and other assets.
| FINANCE MANAGER |  | Responsible:
| Carol Fox |  | Monitor procurements and resource planning
Monitor cash flow balance.
KEY MILESTONES
| START |  | PROJECT PLANNING
| Jan 2024 - Jan 2024 |  | This phrase will include planning and preparation tasks. We'll plan the scope and task breakdown. Also, the budgeting and resource planning will be planned in this stage. The full planning will be prepared and reported to the top management before the final approval.
| PREPERATION |  | PROJECT PREPARATION
| Jan 2024 - Feb 2024 |  | We'll dive deeper into planning strategies here. We'll make the schedules. We'll also finalize hirings for human resources gaps. We'll have calls with suppliers and finalize the possible procurements.
| EXECUTION |  | PROJECT EXECUTION
| Feb 2024 - Feb 2024 |  | This is the execution stage of the project. We'll complete the tasks. The monitoring is very important in this stage. We'll also track the whole progress with a risk management perspective. All the stages here will be reported weekly to the top management.
| FINAL |  | FINALIZATION
| Mar 2024 - Mar 2024 |  | We'll finalize the entire project here. The team will hold the quality assurance tests. We'll also make sure that all documentation is ready for both technical and administrative parts. After completing the final review, we'll prepare the last reports.
RISK EVALUATION
| Risks | Impact Level | Likelihood | Action | Owner
| Delay in HR | Medium | Likely | Outsourcing | Mary Gear
| Incorrect use of equipment | High | Unlikely | Instructions | Terry Johnson
NOTES & COMMENTS
This report is the first of the coming regular reports.
The planning of the project has been started and the resource planning is coming to an end. We'll deal with other planning issues for the coming reporting period.
Back to
Menu

## Gantt
PROJECT PLAN TEMPLATE
GANTT VIEW
Month | January |  | Completed |  |  |  |  | In-Progress |  |  |  |  | Not Started |  |  |  |  | Non-defined | [15 empty] | NEXT MONTH: 2024 / February
Year | 2024
|  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Phrase | Task | Assigned To | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Phase 1 | Define Scope | Alice
Phase 1 | Identify Stakeholders | Bob
Phase 2 | Create Schedule | Charlie
Phase 2 | Resource Planning | Diana
Phase 3 | Task Execution | Entire Team
Phase 3 | Monitor Progress | Emma
Phase 3 | Risk Management | Frank
Back to
Menu

## Dashboard
PROJECT PLAN TEMPLATE
DASHBOARD
| Project Starts |  | Project Ends
| 2024-01-01 | 34 DAYS | 2024-02-04
TOTAL TASKS
7
COMPLETED
BUDGET
178000
SPENT
123000
Back to
Menu

## Calc (hidden)
General Task Table | [10 empty] | General Gantt Settings for Conditional Fortmatting | [65 empty] | Dashboard Calculations | [6 empty] | General Settings and Drop-Down Menus
[11 empty] | First Month | [32 empty] | Second Month |  | 2024 / February
[11 empty] | Month | 1 | [31 empty] | Month | 2
[11 empty] | Year | 2024 | [31 empty] | Year | 2024
[11 empty] | Month Day | 31 | [31 empty] | Month Day | 29
[13 empty] | 2024-01-01 | 2024-01-02 | 2024-01-03 | 2024-01-04 | 2024-01-05 | 2024-01-06 | 2024-01-07 | 2024-01-08 | 2024-01-09 | 2024-01-10 | 2024-01-11 | 2024-01-12 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-17 | 2024-01-18 | 2024-01-19 | 2024-01-20 | 2024-01-21 | 2024-01-22 | 2024-01-23 | 2024-01-24 | 2024-01-25 | 2024-01-26 | 2024-01-27 | 2024-01-28 | 2024-01-29 | 2024-01-30 | 2024-01-31 |  |  | 2024-02-01 | 2024-02-02 | 2024-02-03 | 2024-02-04 | 2024-02-05 | 2024-02-06 | 2024-02-07 | 2024-02-08 | 2024-02-09 | 2024-02-10 | 2024-02-11 | 2024-02-12 | 2024-02-13 | 2024-02-14 | 2024-02-15 | 2024-02-16 | 2024-02-17 | 2024-02-18 | 2024-02-19 | 2024-02-20 | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02
Column Index | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |  |  |  | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed |  |  | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat
Row Index | Phase | Tasks/Deliverables | Description | Priority | Assigned To | Start Date | Duration [Days] | End Date | Status | Status Code |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | PROJECT DATES |  | TASK INFO BOXES |  | BUDGET INFO BOXES |  |  | Month | Order | Month Day | Order | Days | Abbr. | Status | Code | Color | Priority
1 | Phase 1 | Define Scope | Determine project scope and goals | Low | Alice | 2024-01-02 | 5 | 2024-01-06 | Not Started | 1 | [66 empty] | Project Starts | 2024-01-01 | Total Tasks | 7 | Budget | 178000 |  | January | 1 | 31 | 1 | Sunday | Sun | Not Started | 1 | #A3CEF1 | Low | bar: 2024-01-02 to 2024-01-06
2 | Phase 1 | Identify Stakeholders | List all stakeholders | Medium | Bob | 2024-01-01 | 3 | 2024-01-03 | In-Progress | 2 |  |  | 2024-01-01: 2; 2024-01-02: 2; 2024-01-03: 2 | [33 empty] | Project Ends | 2024-02-04 | Completed |  | Spent | 123000 |  | February | 2 | 29 | 2 | Monday | Mon | In-Progress | 2 | #6096BA | Medium
3 | Phase 2 | Create Schedule | Develop project timeline | High | Charlie | 2024-01-07 | 7 | 2024-01-13 | Completed | 3 |  |  | 2024-01-07: 3; 2024-01-08: 3; 2024-01-09: 3; 2024-01-10: 3; 2024-01-11: 3; 2024-01-12: 3; 2024-01-13: 3 | [33 empty] | Duration | 34 | [5 empty] | March | 3 | 31 | 3 | Tuesday | Tue | Completed | 3 | #02C39A | High
4 | Phase 2 | Resource Planning | Allocate resources | Low | Diana | 2024-01-08 | 5 | 2024-01-12 |  | 4 |  |  | 2024-01-08: 4; 2024-01-09: 4; 2024-01-10: 4; 2024-01-11: 4; 2024-01-12: 4 | [35 empty] | STATUS |  |  |  |  | April | 4 | 30 | 4 | Wednesday | Wed | Non-defined | 4 | #D9D9D9
5 | Phase 3 | Task Execution | Execute project tasks | Medium | Entire Team | 2024-01-15 | 20 | 2024-02-03 | Completed | 3 |  |  | 2024-01-15: 3; 2024-01-16: 3; 2024-01-17: 3; 2024-01-18: 3; 2024-01-19: 3; 2024-01-20: 3; 2024-01-21: 3; 2024-01-22: 3; 2024-01-23: 3; 2024-01-24: 3; 2024-01-25: 3; 2024-01-26: 3; 2024-01-27: 3; 2024-01-28: 3; 2024-01-29: 3; 2024-01-30: 3; 2024-01-31: 3 |  |  | 3 | 3 | 3 | [30 empty] | Not Started | 2 | BUDGET DOUGHNUT |  |  | May | 5 | 31 | 5 | Thursday | Thu
6 | Phase 3 | Monitor Progress | Track task progress | Medium | Emma | 2024-01-16 | 20 | 2024-02-04 | Not Started | 1 | [35 empty] | 1 | 1 | 1 | 1 | [29 empty] | In-Progress | 2 | Spent | 69.1% |  | June | 6 | 30 | 6 | Friday | Fri | bar: 2024-01-16 to 2024-01-31
7 | Phase 3 | Risk Management | Identify and mitigate risks | High | Frank | 2024-01-20 | 10 | 2024-01-29 | In-Progress | 2 |  |  | 2024-01-20: 2; 2024-01-21: 2; 2024-01-22: 2; 2024-01-23: 2; 2024-01-24: 2; 2024-01-25: 2; 2024-01-26: 2; 2024-01-27: 2; 2024-01-28: 2; 2024-01-29: 2 | [35 empty] | Completed | 2 | Remaining | 30.9% |  | July | 7 | 31 | 7 | Saturday | Sat
8 | [78 empty] | Non-defined | 1 |  |  |  | August | 8 | 31
9 | [83 empty] | September | 9 | 30
10 | [80 empty] | EXPENSES | Budget | Spent | October | 10 | 31
[79 empty] | PRIORITY |  | Labor | 55000 | 12000 | November | 11 | 30
[79 empty] | Low | 2 | Marketing | 43000 | 22000 | December | 12 | 31
[79 empty] | Medium | 3 | Equipment | 20000 | 22000
[79 empty] | High | 2 | Hardware | 50000 | 60000
[81 empty] | Software | 10000 | 7000 | ROW NUMBERS
[82 empty] | 0 | 0 | Gantt Row Height | 7
[82 empty] | 0 | 0 | Tasks Print Raw | 7
[82 empty] | 0 | 0 | Budget Print Raw | 8
[82 empty] | 0 | 0 | Tasks Print Col | 9
[82 empty] | 0 | 0 | Budget Print Col | 8
[81 empty] | Category # | 5 |  | Phase Number | 5